## Sheet1
| Responsible | 2022-11-19 | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12
Phase 1 - Finalizing the scope
Market and Time and Currency and Twitter guys | Keerthi / Shivaani | bar: 2022-11-19
Mock up Preparation | Asad / Pranav | bar: 2022-11-19
Researching on Literature | ALL | bar: 2022-11-19
Checking Data Sources
Twitter | Keerthi / Shivaani | bar: 2022-11-19
Binance / Alpha Vantage / Coingecko / Coinbase | Keerthi / Shivaani | bar: 2022-11-19
Yahoo Finance | Asad / Pranav | bar: 2022-11-19
Coin Information / News | Pranav | bar: 2022-11-19
Macroeconomic Indicators - CSV | Asad | bar: 2022-11-19
Call to align @ 9 pm | bar: 2022-11-19
Delivering Project Plan | bar: 2022-11-20
Phase 2
Gathering Data (2021 - 2022)
Macroeconomic Indicators - CSV | Asad | bar: 2022-11-21
Yahoo Finance | Asad | bar: 2022-11-21 to 2022-11-22
Binance / Alpha Vantage / Coingecko / Coinbase (daily Data) | Shivaani | bar: 2022-11-21 to 2022-11-23
Coin Information / News | Asad / Pranav | bar: 2022-11-21 to 2022-11-23
Twitter (Daily Data) | Pranav / Keerthi | bar: 2022-11-21 to 2022-11-26
Integrating Data | bar: 2022-11-25 to 2022-11-26
Sanity Checks | bar: 2022-11-27
Phase 3
Developing tool / Building GUI | ALL | bar: 2022-11-28 to 2022-12-02
Testing GUI | ALL
Delivery & Presentation
Recording a Live Demo | ALL | bar: 2022-12-05 to 2022-12-06
Incorporating last 7/30 day data through API | ALL | bar: 2022-12-07
Making a presentation + buffer | ALL | bar: 2022-12-07 to 2022-12-09
Delivery | ALL | bar: 2022-12-12